## Sheet1
Page | Tasks (Phase 1) : HTML/CSS/JS | Date Completed | Tasks (Phase 2) : PHP/SQL | People Responsible | Deadline
Main (index.html) / General | Link to Registration, packages, and contact (Jasmeen) |  | Import database and link to all pages that need it (Jasmeen) | Jasmeen
| Modular design for easy CSS targeting (Done) |  | Darcie: Add DB to Git and commit
styles.css | Change design (background image, colours) (Leisy) |  | Make sure all new elements have css | Leisy, Jasmeen
Registration | Create a form for a customer to create an account (use JS) with their name, address, phone, userID, password. Data should go to bouncer,php. (Leisy) |  | Convert form to incorporate PHP
Contact | Create static page with information about how to phone, email, or go to the agency (jose) |  | Update to generate the agency information from the database | done
Display information nicely
Vacation Packages | Create a “Vacation Package” page listing all vacation packages available. (static for now) (Darcie) | Tuesday, November 4 | Add PHP that grabs the packages from the database
Display package information nicely
CSS: Start date bold and red
Order Button for each package, opens the order page
Order page | N/A |  | Link to database | Jose
customer data booking record
Extra features (ideas) | Responsive Design for Mobile |  | Use after effects for a video for presentation
| Add booking form (order page) to front page? |  | In presentation talk about the technology