## Sheet1
Page / Feature | Tasks (Phase 1) : HTML/CSS/JS | People Responsible | Date Completed | Tasks (Phase 2) : PHP/SQL | People Responsible | Date Completed | Notes
Main (index.html) / General | Links to Registration, packages, and contact | Leisy | Monday November 10 | Create Functions file, add database connection function | Darcie | Wednesday November 12
| Create page templates, modular design | Leisy | Wednesday November 5 | Export updated DB to Git and commit | Darcie | Sunday November 9
styles.css | Change design (background image, colours) | Leisy and Jasmeen | Wednesday November 5 | Make sure all new elements have css | Leisy | ongoing
Registration | Create a form for a customer to create an account (use JS) with their name, address, phone, userID, password. Data should go to bouncer,php. | Leisy | Friday November 7 | Convert form to incorporate PHP | Leisy | Wednesday November 12
Contact | Create static page with information about how to phone, email, or go to the agency | Jose | Friday November 7 | Generate the agency information from the database | Jose | Friday November 7
Display information nicely
Vacation Packages | Create a “Vacation Package” page listing all vacation packages available. (static for now) | Darcie | Tuesday, November 4 | Add PHP that grabs the valid packages from the database | Darcie | Sunday November 9
|  |  |  | Display package information nicely | Darcie | Sunday November 9
|  |  |  | CSS: Start date bold and red | Darcie | Wednesday November 12
|  |  |  | Order Button for each package, opens the order page | Darcie | Tuesday November 18
Order page | N/A | N/A | N/A | Create an order page for customers to enter their information, with a form | Jose / Jasmeen
|  |  |  | Insert booking record into database | Jose / Jasmeen
Order Confirmation Page |  |  |  | After order is completed, display a confirmation page | Darcie | Thursday November 13
Extra features (ideas) | Responsive Design for Mobile | ? |  | Use after effects for a video for presentation
| Front page booking form | Jasmeen |  | In presentation talk about the technology
Testing | N/A | N/A | N/A | Test all completed pages for functionality, completion of assignment requirements, and consistent professional look, feel, & user experience | Jasmeen / Darcie
|  |  |  | Go through code and make sure everything has an author, consistent comment style, intenting, etc. | Jasmeen, Darcie
Presentation Lead(s): Leisy and Darcie |  |  |  | Create plan for presentation (structure) | Darcie | Sunday November 17
|  |  |  | Create slides for presentation | Darcie | Thursday November 20
|  |  |  | Estimate Costs | Darcie / Jasmeen